## Slide 1: IW:LEARN TDA/SAP Training Course
Module 4: Planning the TDA/SAP Process

## Slide 2: Section 1: Planning and managing the TDA Process

## Slide 3: In this Section you will learn about….
Key TDA milestones
Defining the timeframe for TDA development
Setting up the TDA development team
Meetings and Workshops

## Slide 4: The Key TDA Milestones
Create workplan and budget
Form TDA development team and hire consultants
Training workshop on the TDA/SAP process
Kick off meeting
Causal chain analysis workshop
Development of thematic reports
Thematic report meeting
TDA drafting process
Final TDA review meeting and SAP linkage
Adoption by steering committee

## Slide 5: Managing Expectations
The complexity and level of detail of the TDA and SAP developed during the project will be a reflection of the time, funds and human resources available
It will be necessary to carefully manage the expectations of all key stakeholders in the participating countries and the respective implementing and executing agencies

## Slide 6: TDA Time Frame
Will vary from project to project
Some projects have completed the activity within a year whist other projects can take much longer
Much will depend on the number of participating countries, the complexity of the project and the budget available

## Slide 7: Important!
It is important to remember that the TDA is not the main outcome of the TDA/SAP Process - it’s just one step on the path to develop and endorse the SAP - so ensure the time is used efficiently and effectively

## Slide 8: Indicative TDA Development Times

## Slide 9: TDA Development Team….
….should be a broadly representative technical body that represents the countries participating in the project and that will participate in the key development steps for the TDA
It is important to ensure that the TDA Development Team is representative of all key stakeholders

## Slide 10: Stakeholder Inclusion during the TDA Development Process
If the TDA or SAP development process is captured by a particular stakeholder group or groups, the consensus building process will be compromised
SAP implementation can fail if stakeholders (for example, industries being regulated) are excluded from either the TDA or the SAP development

## Slide 11: TDA Team Make-up
Natural scientists –based on appropriate disciplines for the water system in question
Social scientists – including social assessment/participation experts
Economists – e.g. fisheries economists; environmental economists
Legal experts – water based legislation and regulations
Policy experts – Governance and institutions

## Slide 12: Representation and Size
It is important that the TDA Development Team is well represented by all the above groups
Often, it is difficult to find suitable economists
In contrast, it is usually easy to find willing natural scientists, and it is tempting to form the Development Team from this group
Approximately 10 – 20 group members

## Slide 13: Meetings and workshops
A series of meetings or workshops are likely to be held during the TDA development phase
The number and style will vary from project to project according to the time, funds and human resources available

## Slide 14: Example
Training Workshop on the TDA/SAP process
TDA Inception Meeting
Causal Chain Analysis Workshop
Thematic or National Report Meeting
TDA Review Meeting

## Slide 15: Section 1: Planning and managing the SAP Process

## Slide 16: In this Section you will learn about….
Key SAP milestones
Defining the timeframe for SAP development
Setting up the SAP development team
Meetings and Workshops

## Slide 17: The Key SAP Milestones
Develop workplan and budget
Form SAP development team and hire consultants
Training workshop on the TDA/SAP process
Strategic thinking workshop 1 (visions and goals)
Strategic thinking workshop 2 (Ideas, opportunities and options)
National and regional consultation process
SAP drafting process
Final SAP review meeting
SAP endorsement

## Slide 18: SAP Time Frame
Will vary from project to project
Some projects have completed the activity within a year to 18 months whist other projects can take much longer
Much will depend on the number of participating countries, the complexity of the project and the budget available

## Slide 19: Important!
Process might span more than one GEF intervention…
e.g. the SAP document, or a technical draft of the SAP might be produced during one GEF project, along with the TDA, whilst further SAP development, endorsement and implementation might occur during subsequent projects

## Slide 20: Indicative SAP Development Times

## Slide 21: SAP Development Team….
….should be a broadly representative technical body that represents the countries participating in the project and that will participate in the key development steps for the SAP
It is important to ensure that the SAP Development Team is representative of all key stakeholders

## Slide 22: Stakeholder Inclusion during the SAP Development Process
If the TDA or SAP development process is captured by a particular stakeholder group or groups, the consensus building process will be compromised
SAP implementation can fail if stakeholders (for example, industries being regulated) are excluded from either the TDA or the SAP development

## Slide 23: Representation and Size
The make up of the Development Team should be as interdisciplinary as possible.
In particular, the Team will need good economists, policy, and legal experts – these specialists are likely to play key roles in the SAP development
In general the SAP Development Team will number between 10 and 20 participants

## Slide 24: Meetings and workshops
A series of meetings or workshops are likely to be held during the SAP development phase
The number and style will vary from project to project according to the time, funds and human resources available

## Slide 25: Example
Training workshop on SAP Development
Strategic thinking workshop 1: vision and goals
Strategic thinking workshop 2: ideas and opportunities and setting options
National consultation meetings
SAP action planning meeting
SAP Review meeting

## Slide 26: Group Exercise
In groups of 5:
  To be defined
Timing: 20 minutes