## Slide 1: IW:LEARN TDA/SAP Training Course
Module 3: Developing the SAP

## Slide 2: Overview of the Training Course
4 Modules:
  Module 1: Introduction
  Module 2:Developing the TDA
  Module 3: Formulating the SAP
  Module 4: Managing the TDA/SAP process

## Slide 3
Overview of Today
AM
  Opening
  Module 3: Developing the SAP - Identifying Goals
  Group Exercise
  Module 3: Developing the SAP - Brainstorming Innovative Ideas
  Group Exercise
  Module 3: Developing the SAP - Prioritising Options or Alternatives
  Break
  LUNCH
PM
  Module 3: Developing the SAP - National and Regional Processes
  Group Exercise
  Module 3: Developing the SAP – Drafting the SAP
  Module 4: Planning the TDA/SAP Process
  Summary and Wrap Up of TDA/SAP Training Course
  Break
  END

## Slide 4: Section 10: Action Planning: Setting actions, timescales, priorities and indicators

## Slide 5: Where are we?
Implementing strategies
Setting strategic actions
Drafting the SAP
National and Regional consultation

## Slide 6: In this Section you will learn about….
What is an Action Plan?
What does Action Planning mean in terms of the SAP?
Key Action Planning Steps

## Slide 7: What is an Action Plan?
An action plan is a framework of objectives and actions for achieving strategy goals
It should state clearly how each action contributes to one or more given objective and may suggest a relative rating (e.g. high, medium or low)

## Slide 8: What does Action Planning mean in terms of the SAP?
One of the core outcomes when drafting a SAP is to develop it in a way that is easily translatable into action
The SAP should address not only the high-level initiatives and over-arching goals, but that they get articulated into short term actions that will be required to achieve the programme.
Key to this step is the translation of the agreed options and alternatives into Objectives and Actions. This step will need to be carefully managed by the Project Manager and the SAP Development Team

## Slide 9: What are Goals and Objectives?
  …are general guidelines that explain what you want to achieve in your water system - they are usually long-term and represent global visions such as “reduce pollution by…..” or “increase biodiversity by…..”.
Goals…
  …define strategies or implementation steps to attain the identified goals. Unlike goals, objectives are specific, measurable, and have a defined completion date.
Objectives…
  …Often, each objective is associated with a series of actions. Therefore, implementing a strategic goal typically involves implementing a series of actions along the way.
Actions…

## Slide 10: Key Action Planning Components
Goals
Objectives
Actions
Time required for implementation
Financing requirement.
Priority
Stakeholders involved
Indicator of success
Uncertainties

## Slide 11: Section 11: Drafting the SAP

## Slide 12: Where are we?
National and Regional consultation
Implementing strategies
Setting strategic actions
Drafting the SAP

## Slide 13: In this Section you will learn about….
Integration of the component parts of the SAP
Advice from the field: What should a SAP look like?
Steps towards SAP implementation

## Slide 14
TDA
Document
Vision
Statement
Leverage
points
Goals
  Options and alternatives
Action Plan
Outputs
Implementation
Strategies
Indicators of
success
Legal and
Institutional

## Slide 15: Integration of the component parts of the SAP
All this information now needs to be integrated into one document
The appointment of a consultant, specialist, academic, or a consultancy to act as a single author reporting to the Project Manager (e.g. Lake Chad SAP, Nubian Aquifer SAP)
Appointment of key SAP development team members to draft individual Chapters of the SAP, with an appointed Manager acting as a focal point reporting to the Project Manager (e.g. Black Sea SAP, Dnipro River Basin SAP, Rio de la Plata TDA

## Slide 16: Both approaches work…..
Appointing an individual or consultancy to draft the SAP is generally quicker and more efficient but there is a loss of stakeholder involvement and collaboration.
Drafting the TDA using a team can be more demanding on time, funds and energy but is generally a more collaborative process.

## Slide 17: What should a SAP look like?
There is no single approach or model used for the SAP document structure.
it should be concise and jargon-free
It should contain:
  Clear goals and prioritised actions
  Quantifiable time-limited milestones and unambiguous assignment of responsibilities

## Slide 18: Possible Sections
An undersigned agreement
Executive summary
Description of the water system
A statement of the priority problems taken from the TDA
Principles adopted for solving them
Rationale and opportunities for regional cooperation
Any joint planning and dispute settlement mechanisms
Institutional arrangements
Any policy and legal reforms
Public participation strategies
The vision, goals and priority actions
Monitoring and review arrangements and reporting

## Slide 19: What should a SAP look like?
Executive Summary
Decision makers will not read the entire document
Concise and jargon-free
A good executive summary will promote the SAP
The main text
Keep it coherent and concise - an overly long document will be difficult to navigate and interpret
Don’t present too much text or equally too many figures and tables
Supporting data (either figures or tables) can be presented in separate Annexes

## Slide 20: What should a TDA look like?
Language
Generally, SAPs are written in the predominant UN language for the region
If the SAP is not written in English, it is likely a translation will be needed
Useful to hire a native English expert to fully edit the translated document
SAP for decision - makers
A shortened version of the full SAP can also be produced.
It provides a long executive summary, together with visuals and graphics summarising how the SAP will benefit the water system and the participating countries.

## Slide 21: What should a TDA look like?
Content List
Provide a Content List and a Glossary of all terms employed
Make sure the pages are numbered and the content list numbering corresponds with the page numbering – this is a common and annoying mistake.
Technical Reports
Complex technical reports should be published separately or as annexes.
Acknowledgements
Include a full list of contributing specialists, and annexes containing lists of identified stakeholders.
Approximate size
The size of the SAP will vary from project to project and from water type to water type.
Typically it should be between 80 and 150 pages (plus annexes)

## Slide 22: Steps towards SAP Implementation
The draft SAP document should be thoroughly reviewed by the SAP development team and key stakeholders to ensure it is:
  Fit-for-purpose;
  At a stage to be adopted by the project steering committee; and
  Likely to be endorsed by the participating countries.
  It is advisable to ensure that copies of the SAP document are circulated well in advance of this meeting to ensure the review process is successful.

## Slide 23: Endorsement
The steps towards SAP endorsement will be different for each project and the process can quite often be difficult and time-consuming
However, to ensure that the process is as straightforward as possible, it is important to carefully coordinate the steps towards endorsement

## Slide 24: Endorsement
This could include the arrangement of high-level meetings during the SAP development phase with senior officials from the key ministries in each country to ensure that there is general consensus towards the SAP and its endorsement

## Slide 25: So that is the TDA/SAP Process…

## Slide 26: Within the Framework of Adaptive Management